## 📋 Projects
TGM EDUCATION — R&D PROJECT TRACKING SHEET
R&D Division ¦ Last Updated: 15 May 2026 ¦ Confidential
Project ID | Project Name | Project Description | Project Owner / Team Lead | What has been doen | Current Status | % Complete | Start Date | Deadline / Due Date | Risks / Challenges and Follow-up | Next Action Step | KPI / Success Metric
RD-001 | Bot Building | Smart AI chatbots built to engage students interested in studying abroad, answer their questions, and guide them toward applying. We currently have 8 active bots — one each for TGM, Advisors Academy, RGU, Kent, Northampton, UCLan, Swansea and Navitas[ICP]. | Totan/Chi | ~ 8 bots built and fully deployed ~ All bots are live and actively running ~ Each bot connected to its respective institution ~ Bots are responding to student enquiries in real time | in Progress | 100% | june | Completeed | Bot accuracy & tone consistency across 8 institutions; ongoing maintenance; CRM integration gaps | Optimise lead conversion flows; integrate CRM for lead tracking & reporting | No. of leads generated per bot per month
RD-002 | Advisors Academy | An online education platform where students explore universities and courses from around the world, get matched to the right programme, and receive expert guidance through their application journey. Advisors use the same platform to manage student enquiries and placements. | Totan | ~ Website fully built and live at advisors.academy ~ All dashboards are functional and working ~ Mobile app development completed ~ App deployment currently in progress | In Progress | 90% | 23/02/2026 | 29/05/2026 | University data accuracy & timely updates; counsellor availability; student adoption & engagement rate | Expand university partnerships & launch student agent recruitment campaign | Monthly active users; applications submitted via platform
RD-003 | HR App | A digital HR dashboard that manages everything that happens after a staff member joins TGM — from onboarding and contracts to leave, appraisals, payroll support and offboarding. Replaces manual paperwork with one clean system for the HR team. | Victor/Totan | ~ Platform is actively being built and progressing well ~ Employer-facing dashboard is functional and improving ~ Applicant management system is live — employers can view, search and manage candidates ~ Document handling in place — CVs and cover Letters accessible and downloadable ~ Candidate tracking system built — full visibility of all applicants across all job listings ~ UI and workflow improvements ongoing for a cleaner user experience | In Progress | 70% | 27/04/2026 | Undecided | Data migration from manual records; staff adoption & training; data privacy compliance (NDPR) | Final QA testing & company-wide staff onboarding training session | Reduction in manual HR processing time; staff adoption rate
RD-004 | Roadshow Registration Dashboard | A management system for TGM's student recruitment roadshow events. It handles registrations, attendee tracking, check-ins and post-event reports; making it easy to run large-scale events across multiple cities without spreadsheets or manual sign-ups. | Totan | ~ Proof of consent completed and validated ~ Pre-registration system is live and working ~ Email notifications set up and sending ~ Check-in functionality built ~ Core dashboard features developed ~ Additional features such as attendee management, analytics and event coordination are in place" | In Progress | 50% | Undecided | 26/06/2026 | High-traffic scalability during peak events — RESOLVED with cloud hosting | Plan V2 with SMS notifications, self-check-in kiosk & WhatsApp reminders | Registrations processed; no-show rate reduction; event NPS score
RD-005 | TGM Travels | A flight booking app built by TGM; like Uber, but for flying. Travellers can search, compare and book flights, manage their trips and get support all in one place. Designed to make air travel as simple and seamless as ordering a ride. | Victor | • Completed selecting a course for a student • Started working on TGM travels {Admin pages, Autenctication page, login, dashboard and flights} | In Progress | 30% | Undecided | Undecided | GDS/airline API integration costs; regulatory compliance; competitive market; budget approval | Finalise product requirements, choose tech stack & secure budget approval from board | Bookings per month; revenue generated; customer acquisition cost
RD-006 | Application Hub (Application Dashboard) | An internal dashboard for the application department. Counsellors and application officers use it to submit and track student applications, apply to more than one school at once, get notifications, and run reports. Includes a separate admin portal for management oversight. | Chi | ~ Counsellor and Application Officer portals built and working ~ Multi-school application submission enabled ~ Notification feature added ~ Admin portal created ~ Round-robin officer assignment in place ~ Deployment and UI changes ongoing | In Progress | 60% | 18/05/2026 | Undecided | Duplicate student rows on counsellor dashboard; university autocomplete limits; deployment stability | Finish deployment testing, resolve duplicate rows and roll out to the full application team | Applications processed per officer; reduction in manual tracking time
RD-007 | Executive One Dashboard & Bot | A reporting dashboard and supporting bot built for executive-level oversight. It pulls together filtered and cleaned company data so leadership can view key figures in one place, with a bot handling enquiries and form collection. | Totan/Chi/Dami | ~ Dashboard deployment started ~ Data filtering and cleaning completed ~ Executive One bot configured (forms integration, email collection and verification) ~ Dashboard cleaned up and refined | In Progress | 50% | 17/06/2026 | Undecided | Data accuracy and cleaning effort; bot response quality; email verification automation still in progress | Finalise bot automation, complete dashboard polish and present to leadership | Reporting turnaround time; executive adoption
RD-008 | AI Policy Checker | An internal tool that checks content and bot responses against TGM policy. It helps keep messaging consistent and compliant across the bots and the Advisors Academy platform. | Totan | ~ New AI policy checker created ~ Finished and applied to Advisors | Completed | 100% | 15/06/2026 | 16/06/2026 | Keeping policy rules current as guidelines change | Monitor in use and update rules as policies evolve | Policy issues caught before publishing
RD-009 | In-House Counsellor Bot | An internal AI bot built for TGM counsellors to use directly. It is trained on counsellor chat data and partner-school information so staff can get quick, accurate answers while advising students. | Dami/Chi | ~ Bot being built and trained on counsellor chat data ~ TGM partner-school course and fee data gathered and loaded ~ Conversation training ongoing using real counsellor chats | In Progress | 90% | 04/06/2026 | Undecided | Quality of training data; keeping course and fee information up to date; counsellor adoption | Continue training, test responses with counsellors and refine knowledge base | Counsellor usage rate; accuracy of bot answers
RD-010 | Pro-posed Project: AI Travel Assistant | A proposed AI tool that automates travel planning and booking from a single chat. A traveller simply tells the bot where they want to go and it instantly suggests options for flights, hotel reservations and full travel itineraries, with prices, so they can pick the option that fits their budget. It handles the planning and booking end to end, making travel arrangements quick and effortless. | Dami | - Getting the knowlege needed to build it ~ Concept and use case defined (automating the international travel process) | Not Started | 10% | Undecided | Undecided | Scope and budget approval; overlap with TGM Travels; requirement gathering still needed | API Keys | Students supported through travel process; time saved
RD-011 | Portsmouth Bot | A smart AI chatbot built for the University of Portsmouth (ICP) partnership to engage prospective students, answer course and admission enquiries, and guide them toward applying through TGM. It is the 9th bot in the partner-bot network, with custom prefill links and dynamic conversational flows. | Dami/Chi | ~ Bot created and configured in Botpress ~ Conversational flows and structural logic built per Dr. Tolu's guidelines ~ Custom link with prefill message created ~ Data collection completed for courses ~ Presented to stakeholders with the R&D team ~ Number-capture workflow configured | In Progress | 90% | 24/06/2026 | Undecided | Template message delivery to every number; ongoing conversational-flow tuning; keeping course data current | Finalise optimisation and feature-locking, complete stakeholder sign-off and move to full production | No. of leads generated; enquiry response accuracy
RD-012 | Caravan (Events Platform) | An events management platform for creating and running events, with separate portals for event owners and event creators. Includes a public landing page, admin and super-admin dashboards, a speaker feature and security controls. Built to support TGM's large-scale event and exhibition operations. | Victor | ~ Landing page created ~ Admin dashboard built ~ Event owner and event creator admin dashboards built ~ Speaker feature added ~ Security updates applied ~ Super-admin dashboard major updates completed ~ Platform deployed and reviewed with the team | In Progress | 70% | 29/06/2026 | Undecided | Scalability during peak events; feature completeness for owners vs creators; ongoing security hardening | Complete super-admin refinements, finalise remaining admin features and prepare for live events | Events created; registrations processed; platform uptime
RD-013 | Finance Dashboard | An internal finance platform that helps TGM manage and track commission owed from partner schools, alongside broader finance and legal reporting. Gives the finance and leadership teams a single view of commissions, records and key financial figures. | Totan/Victor/Dami | ~ Finance dashboard created for commission tracking from partner schools ~ Dashboard deployed (Finance app live) ~ Admin and super-admin dashboards updated ~ Ongoing changes and updates with the finance/legal team | In Progress | 70% | 30/06/2026 | Undecided | Data accuracy of commission records; integration with partner-school data; access control and privacy | Finalise remaining finance/legal features, validate commission figures and roll out to finance team | Commission tracked vs collected; reporting turnaround time
RD-014 | Customer Service Platform | An internal dashboard for the customer service team that centralises enquiry handling and integrates Jotform submissions for lead capture and follow-up. Built to streamline how customer service manages and routes incoming enquiries. | Totan | ~ Platform actively being built ~ Jotform integrated into the customer service dashboard ~ Meetings held with CS lead (Josephine) on requirements ~ Ongoing follow-up and refinement | In Progress | 50% | 13/07/2026 | Undecided | Requirement clarity with CS team; Jotform-to-CRM data flow; staff adoption | Complete core features, finalise Jotform/CRM flow and hand over to the customer service team | Enquiry resolution time; leads captured via platform
RD-015 | Report Hub | An internal R&D reporting tool that centralises the team's daily accomplishment logs and activity reporting in one place, replacing manual tracking-sheet updates. Built for the R&D department to capture and review daily technical activities. | Chi | ~ New project initiated for the R&D department ~ Core reporting structure built ~ Designed to consolidate daily team reporting | In Progress | 40% | 13/07/2026 | Undecided | Team adoption vs the existing tracking sheet; keeping entries consistent; report accuracy | Complete build, test with the R&D team and roll out for daily use | Daily reporting compliance; time saved on manual updates
RD-016 | Job Locale | A local job board platform (structured like Indeed) built for Mr. Dotun, where employers can post roles and job seekers can search and apply. Developed and refined by the R&D team as an external client project. | Chi/Dami/Totan | ~ Initial prototype designed and built, running in a local environment ~ UI and structural enhancements applied ~ Major updates and refinements executed ~ Domain name purchased for the platform | In Progress | 50% | 07/07/2026 | Undecided | Scope and client sign-off; hosting/deployment; feature completeness vs Indeed-style expectations | Deploy to the purchased domain, complete remaining features and hand over to Mr. Dotun | Job posts created; applications submitted; active users
RD-017 | October 2026 Campaign Bot | A dedicated WhatsApp campaign bot for TGM's October 2026 International Study Exhibition. It engages prospective attendees, answers exhibition and application questions, guides students through starting their application (documents and submission link) and includes a human-handoff procedure. | Dami/Totan | ~ Campaign bot created and trained ~ WhatsApp Manager account set up for the campaign number ~ Learning added for exhibition details and application start flow ~ Human-handoff (human-in-the-loop) procedure added ~ Migration flow built for the campaign bot | In Progress | 70% | 29/07/2026 | 13/10/2026 | Template approval and delivery at scale; accuracy of exhibition info; handoff coverage during peak volume | Finalise learning, test broadcast delivery and go live ahead of the October exhibition dates | Attendees engaged; applications started via bot; response accuracy
RD-018 | TGM Community | A new community platform being built for TGM to connect students, counsellors and partners in one shared space. Currently in early development by the R&D team. | Totan/Dami | ~ New platform initiated ~ Early development work started ~ Learning on deployment (DigitalOcean) undertaken | In Progress | 20% | 29/07/2026 | Undecided | Scope and feature definition; deployment infrastructure; adoption strategy | Define full scope, build core features and set up deployment | Active community members; engagement rate

## ✅ Daily Log
TGM R&D - DAILY ACCOMPLISHMENT LOG
Updated daily by R&D Team
. Monday, 18 May 2026 (Today)
Person | What Was Done | TO-DO
Totan | • Meeting with RGU Team and Mr. Donald on RGU bot review • Advisors Academy application setup • General Meeting with advisors academy team • Fixing bot nudge and response time • Creating a seamsless dashboard for application team • Instructing Chi on how to build ai tools and dashboards
Victor | • Tested advisors mobile app • Started working on custom questiobs for HR website • Completed the publishing for word press • Completed landing page for bot - fix an issue-corrupted file error
Chi | • AI Bot review • Created a seamless dashboard for Application department • Imported UCLAN and Northampton leads • Create a google sheet to our progress track all projects • Learnt how to create a seamsless dashboard using python and ai tools
. Tuesday, 19 May 2026
Person | What Was Done | TO-DO
Totan | • Meeting with Mr. Donald on bot setup for Navitas AI bot review • Advisors Academy systems check • Implemented changes with Victor on Advisors Academy (Counselors can now upload document and Super admin changes completed) • Updated Apple & Android requirements for app upload. • Meeting with Jimmy on how to update and use the blog posting
Victor | • Counselors upload documents for students • Status change for questionnaires on admin • Failing endpoint for mobile app • Refactor emails for counselors • Added HR application questions
Chi | • AI Bot review • Created a seamless dashboard for Application department • Designed R&D Organizational Organogram • Integrated whatsapp update on all the AI bots • Imported UCLAN and Northampton leads • Created an additional tab to the google sheet for daily login activities.
. Wednesday, 20 May 2026
Person | What Was Done | TO-DO
Totan | • Created a list of testers for advisors academy for google play [5] | Create a list of testers for advisors academy for google play Complete the list of the testers
Victor | • Worked on the Advisors Academy website to enable counsellors select schools for students when creating applications • Fixed the file size constraint issue affecting document uploads on the Advisors Academy website. • Tested HR features on the HR website (pending deployment). • Deployed the document upload flow for counsellors on the Advisors Academy website. (pending)
Chi | • Ai bot review, corrected some minor responses on some of the ai bots • Created a dashboard for application team such that application officers and counsellors have access to it | • Update leads for RGU, UCLAN, KENT, Northampton
. Thursday, 21 May 2026
Person | What Was Done | TO-DO
Totan | • Worked with Victor to apply updates on Advisors Academy, including super admin modifications and enabling counselors to upload documents. • Conducted a systems review/check for Advisors Academy. • Revised the requirements needed for Apple and Android for Advisors app
Victor | • Deployed the document upload flow for counsellors on the Advisors Academy website. (pending)
Chi | • Extracted top-up programmes for the uniersities in UK that TGM is in patnership with. • Corrected notification feature and added access to counsellors portal to apply for more than 1 school to application officer | Finish data extraction of top-up programs
. Friday, 22 May 2026
Person | What Was Done | TO-DO
Totan | • Guided Chi on the process of developing AI tools and dashboard systems. • Worked on improving bot response speed and fixing nudge-related issues. • Participated in a general discussion with the Advisors Academy team. • Set up the Advisors Academy application system. • Supervised the dashboard corrections by Chi for the application team.
Victor | • Completed selecting a course for a student • Started working on TGM travels {Admin pages, Autenctication page, login, dashboard and flights} Current link: https://tgmtravels.org/services/ • Meeting with Advisors Academy general counsellors concerning the update on the website | Design a landing page for tgm travels: https://tgmtravels.org/home/
Chi | • Corrected notification feature and added access to counsellors portal to apply for more than 1 school to application officer • Updated the tracking sheet while having a meeting with Victor and Totan
. Monday, 25 May 2026
Person | What Was Done | TO-DO
Totan | • Botpress monitoring and optimization • Follow-up on Advisors team (at the back) on new leads and campaign • Had a meeting with the HR • Creating proof of consent for HR Dashboard
Victor | • Completed Admin design for TGM Travel Admin • Added the configuration for TGM Travels Website Maintenace Mode • Configuring Amadeus and Galileo for flight search • Designed landing page for TGM Travels
Chi | • Import, download and upload of UCLAN, Northampton and KENT leads • Updated the tracking sheet while having a meeting with Victor and Totan • AI Bot review: updated knowledge base of Northampton regarding MRes
. Tuesday, 26 May 2026
Person | What Was Done | TO-DO
Totan | • Botpress monitoring optimization • Follow-up on Advisors team[at the back] on new leads and campaign • Had a meeting with HR • Created proof of consent for HR dasboard
Victor | • Integrate Amadeus to the TGM Travels platform in order to search for flight rates
Chi | • Import, download and upload of RGU leads • AI Bot Review • Updated the tracking sheet while having a meeting with Victor and Totan | • Import, Download and Upload RGU Leads
. Wednesday, 27 May 2026
Person | What Was Done | TO-DO
Totan | PUBLIC HOLIDAY - Children's Day
Victor
Chi
. Thursday, 28 May 2026
Person | What Was Done | TO-DO
Totan | PUBLIC HOLIDAY - Ileya
Victor
Chi
. Friday, 29 May 2026
Person | What Was Done | TO-DO
Totan | • Implementing botpress regarding integration for hubspot • Having meeting with adisors team • Advisors database optimization
Victor | • Integrate Amadeus to the TGM Travels platform in order to search for flight rates • Reach out to TGM Travels Rep to get the details for the integration for Galileo
Chi | • Deployment for application hub has started • AI Bot Review • Work on Swansea bot concerning hubspot integration
Dami | • Setup hubspot integration • Closed ot Advisors Academy leads from previous department • Helped train the bots • Got introduced to advisors database
. Monday, 1 June 2026
Person | What Was Done | TO-DO
Totan | • Supervised hubspot integration for TGM bot • Follow up on leads in jotsform • Presentation with University of Hall • A follow-up meeting with Advisors Academy [at the back]
Victor | • Update on HR platform to add users • UI Update on HR platform • Updated on application stats on HR platform • Remove email notification for certain status on HR application • Confirgure default email templates (status that have email) on HR application
Chi | • Imported, Downloaded and Uploaded UCLAN & North Leads • Updated the tracking sheet while having a meeting with Victor and Totan • Made enquires in the application department for the application dashboard • Update on Application Dashboard and continue process of deployment
Dami | • Hubspot Integration and configuration of response • Imorting of leads for kent • Work on a solution that recommend courses for students [population of data]
. Tuesday, 2 June 2026
Person | What Was Done | TO-DO
Totan | • Apple setup with the developers • Bot configuration with hubspot • Meeting with advisors team[at the back] • Helped Chi to deploy application dashboard • Worked on Advisors databse • Follow-up on customer service leads
Victor | • Completed application status feature • Started deployment for TGM Travels • Worked on minor UI Tweaks on advisors • Added a filter feature on advisors in applicaton section | Application Dashboard for advisors academy
Chi | • Imported, Downloaded and Uploaded RGU & KENT Leads • Updated the tracking sheet while having a meeting with Victor and Totan • Changed the UI interface of the application dashboard and added schools to search • Update on Application Dashboard and continue process of deployment
Dami | • Worked with Totan on Bot Configuration • Responded to Bot escalation to human
. Wednesday, 3 June 2026
Person | What Was Done | TO-DO
Totan
Victor
Chi | • Imported, Downloaded and Uploaded RGU & KENT Leads • Updated the tracking sheet while having a meeting with Victor and Totan • Changed the UI interface of the application dashboard and added schools to search • Update on Application Dashboard and continue process of deployment
Dami
. Thursday, 4 June 2026
Person | What Was Done | TO-DO
Totan | • Meeting with Customer service[Tutu] for Instagram integration of the TGM bot • Meeting with Doctor Tolu concerning Advisrs Academy App
Victor | • Meeting with Doctor Tolu concerning Advisrs Academy App • Worked on TGM Travels making major updates
Chi | • Created a Bot change log for the changes made on all the bots • Updated the tracking sheet while having a meeting with Victor and Totan • Made 8 changes to all the bots and Bot review • Meeting with Doctor Tolu concerning TGM Bot changes • Collation of tuition fees data for TGM bot
Dami | • Created a Bot change log for the changes made on all the bots • Meeting with Doctor Tolu concerning TGM Bot changes • Collation of TGM Data for a new bot for counsellors • Escalated conversation on TGM Bot
. Friday, 5 June 2026
Person | What Was Done | TO-DO
Totan |  | • Data gathering of courses, tuition fees and deposit for 25 universities in UK
Victor
Chi |  | • Data gathering of courses, tuition fees and deposit for 25 universities in UK
Dami | • Made changes on the bot (users that have quick question and directs back to fill the form • Escalated a conversation from the bot about a potential collaboration to the head of IT • Editted a conversational flow for the bot to make more recommendations of universitities outside specified city by the user • Followed up with a previous student from Advisors Academy • Had a presentation with Doctor Tolu and a client | • Data gathering of courses, tuition fees and deposit for 25 universities in UK
. Monday, 8 June 2026
Person | What Was Done | TO-DO
Totan | • Introductory meeting for Kingsley as a new • Corrected a major conversational error on TGM Bot with colleagues • Had a meeting with Mr Donald
Victor | • Meeting with TGM Travels head • Made major UI & flow changes for TGM Travels • Implementation to production and production configuration update • Google sign up and course fee currency for Advisors Academy Website • Had a meeting with TGM Travels Lead on review of TGM Travels and Admin
Chi | • Imported, Downloaded and Uploaded NORTH, UCLAN & RGU Leads • Made changes on TGM bot [correct link to fill and Dependent Requirement] • Overrall onboarding process with Kingsley on all the bots we manage • Review Bot conversation and correct accordingly • Updated infomation on a previous student to the current counsellor • Updated the tracking sheet while having a meeting with colleagues
Dami | • Attended introductory meeting for Kingsley and corrected the major eror on TGM Bot • Enables the vision agent into TGM & RGU Bot • Data gathering for UK Patnerned schools; courses and fees • AI Bot conversation review and made changes accordingly
Kingsley | • Had an introductory meeting with R&D Team • Had anonboarding process with Chiamaka concerning the bot R&D manage • Created an excel sheet for knowledge base for NORTH, Advisors, UCLAN & RGU
. Tuesday, 9 June 2026
Person | What Was Done | TO-DO
Totan | • New design on Advisors Academy • Bot training with team on RGU Bot • Data analysis on CRM against RGU applications to ensure that RGU applications to ensure that there was proper capturing of leads. • Meeting with Graduate Trainees Counsellors under NORTH & UCLAN Leads concerning their current and new upcoming leads from customer service [which was discussed with Branch Manager] • Review of Adv App design & customer journey with Mr Donald
Victor | SICK LEAVE
Chi | • Gathered chat data from Top 3 selected counsellors to improve the bot conversation. • Review Bot conversation and correct accordingly • Updated the tracking sheet while having a meeting with colleagues • Data gathering for UK Patnerned schools; courses and fees
Dami | • Reviewed bot conversations to check for errors or inconsistencies • Added an image and video feature to TGM & RGU's Bot • Gathered chat data from counsellors to train TGM Bot on conversations • Added the vision agent on Kent, ICP, Navitas and Northampton's Bot
. Wednesday, 10 June 2026
Person | What Was Done | TO-DO
Totan | • Bot review on all the bots • Meeting with advisors changes made • Review with Kingsley • General meeting with country manager
Victor | Made changes on Advisors Application • Google sign in and sign up • Updated course fee
Chi | • Gathered chat data from Top 3 selected counsellors to improve the bot conversation. • Review Bot conversation and correct accordingly • Updated the tracking sheet while having a meeting with colleagues • Data gathering for UK Patnerned schools; courses and fees
Dami | • Review of Advisors Academy super admin dashboard and created a document on recommendation • Gathering of data for TGM patner schools • Review of Advisors Academy webapp and testing of it functionalities • Conversation training of TGM Bot with chats gotten from counsellors
. Thursday, 11 June 2026
Person | What Was Done | TO-DO
Totan
Victor
Chi | Fell sick
Dami
. Friday, 12 June 2026
Person | What Was Done | TO-DO
Totan | Democracy Day
Victor
Chi
Dami
. Monday, 15 June 2026
Person | What Was Done | TO-DO
Totan | • Created the new AI policy checker • Meeting with advisors team[at the back] • Had a meeting with Mr Donald • Integration of hubspot with Jotform • Meeting with application officer (Emmanuel) on update of Application Status feature on Adviors
Victor | • Worked on Advisors; storing user choice, course, school and country • From the user selected choice, worked on course and school recommendation
Chi | • Review Bot conversation and correct accordingly • Data gathering for Canada & UK Patnerned schools; courses and fees • Upgraded whatsapp integration on all bots • Worked on testing of deployment of application dashboard • Updated the tracking sheet while having a meeting with colleagues
Dami | • Preposition of a new solution (AI travel assistant). Automating intenational travel process • Worked on integration of hubspot into Jotform to automate contact creation • Gathering of data (courses and fees) for TGM partner schools. • Meeting with Victor on implementation of changes to Advisers SuperAdmin dashboard [Adv] • Review of bot conversations to check for errors in conversational flow.
. Tuesday, 16 June 2026
Person | What Was Done | TO-DO
Totan | • Finished up the AI policy and advisors • Updates advisors database • Had a meeting with Mr Donald • Had a follow-up meeting with Advisors team[at the back] • Meeting GT Kent counsellors concerning their new leads [RGU Leads]
Victor | • Tested the new feature added from yesterday on Adv App • Tested previous implementation • Deployed the Adv App • Worked on SuperAdmin recommendation
Chi | • Review Bot conversation and correct accordingly • Data gathering for Canada & UK Patnerned schools; courses and fees • Enabled translator agents on RGU, NORTH, KENT & UCLAN Bot • Worked on testing of deployment of application dashboard • Updated RGU Leads by GT Kent Counsellors to RGU leads [Oluchi & Adeyinka] • Updated the tracking sheet while having a meeting with colleagues
Dami | • Review of bot conversations to evaluate efficiency and detect errors • Corrected the nudge seequence on Kent bot • Worked with Totan on uploading of newly gathered courses for 4 universities on the advisors portal • Data collection for new partner schools in Canada • Worked on the in-house bot being built for counsellors • Followed up on the recommendations made on advisors super admin • Worked on a walkthrough on Advisros website to make sure all features are working well
. Wednesday, 17 June 2026
Person | What Was Done | TO-DO
Totan | • Worked on deployment of Executive One dashboard
Victor | • Worked on end point and fixes for mobile app for advisors academy • Created a pipline for automatic deploymenent for Advisors Academy • Worked on super admin recommendation
Chi | • Review Bot conversation and correct accordingly • Data gathering for UK Patnerned schools; courses and fees • Data filtering and cleaning for Executive One data • Worked on testing of deployment of application dashboard • Updated the tracking sheet while having a meeting with colleagues. • Upgraded whatsapp integration on all the bots
Dami | • Worked on executiveone bot (configurations and learning) • Responded to bot human hand-off • Assisted Totan on data cleaning • Reviewed bot conversations • Worked on the in-house bot being built for counsellors
. Thursay, 18 June 2026
Person | What Was Done | TO-DO
Totan | • Cleaned up Executive one dashboard • Worked on Botpress • Follow-up with Advisors Team
Victor | • Completed the CICD pipline deployment on Advisors • Worked on super admin recommendation
Chi | • Created an admin portal for applicaton dashboard • Review Bot conversation and correct accordingly • Worked on deployment & UI changes of application dashboard • Data gathering for UK Patnerned schools; courses and fees • Updated & designed profile pictures for RGU, Northampton, Kent & UCLAN Bot whatsapp • Escalated conversation on TGM Bot • Updated the tracking sheet while having a meeting with colleagues
Dami | • Worked on executiveone bot (forms integration, perfecting of response, attempt automation of email collection and verification) • Responded to bot human hand-off • Upload of courses to advisors platform [3 universities] • Reviewed bot conversations • Worked on bot being built for internal use by counselors.
. Friday, 19 June 2026
Person | What Was Done | TO-DO
Totan | • Worked on Exective One dashboard with the executive one team
Victor | • Completed superadmin on Advisors academy • Added new feature to Advisors [charts, filter section, counsellor & admin]
Chi | • Conducted ongoing reviews of active bot conversations and implemented necessary backend corrections. • Sourced a new list of institutions and conducted data gathering of updated courses for the Jan 2026 intake across both Canada and UK schools. • Processed and compiled the graduate data for the Executive One database. • Worked on the newly filtered data for Executive One • Worked with Totan on Executive One records directly onto the live application dashboard.
Dami
. Monday, 22 June 2026
Person | What Was Done | TO-DO
Totan | • Presented the campaign application demo to Mr. Donald and Mr. Bolade, highlighting its key features and functionality • Worked on the Executive One dashboard, contributing to its development and improvement. • Assisted Chi with the deployment process, helping to ensure a successful release.
Victor | • Tested and validated the newly updated features on the Advisors platform. • Identified and resolved three bugs on the Advisors platform. • Worked on implementing updates for the TGM Travels project. • Updated the CICD pipeline to enable automatic deployment for the Admin Executive modules on both Executive One Capital and Advisors.
Chi | • Review Bot conversation and correct accordingly • Deployed the application dashboard • Imported and downloaded RGU leads • Updated the tracking sheet while having a meeting with colleagues
Dami | • Conducted data collection and compilation for Canadian universities and colleges. • Worked on the Executive One bot, including email configuration and confirmation workflows, and enabled the bot to identify new sign-ups and users who have successfully completed forms. • Created and configured the Meta Business Suite account for Advisors Academy. • Reviewed bot conversations to improve performance, accuracy, and user experience. • Contributed to the development of the in-house Counsellor Bot, including UI design, database setup, and system configuration.
. Tuesday, 23 June 2026
Person | What Was Done | TO-DO
Totan | • Worked on Executive One Dashboardd
Victor | • Made a couple of changes on TGM Travels
Chi | • Review Bot conversation and correct accordingly • Deployed the application dashboard • Imported, downloaded, and uploaded new leads RGU, KENT, UCLAN, NORTH • Updated the tracking sheet while having a meeting with colleagues • Upgraded the WhatsApp integrations for all the bots
Dami | • Uploaded updated data courses to Advisors academy • Gathering of updated Jan 2026 courses and fees to update TGM Knowledge base • Review of bot conversations • Review of recommended changes eeffected on advisors super admin dashboard with Victor
. Wednesday, 24 June 2026
Person | What Was Done | TO-DO
Totan | • Created business portfolio • Had a meeting with Doctor Tolu & Victor • Worked on a new bot [Portmouth] with AI Bot team
Victor | • Made a couple of changes on TGM Travels
Chi | • Review Bot conversation and correct accordingly • Escalated a conversation on TGM Bot • Worked on data collection for the new bot [Portsmouth] • Updated the tracking sheet while having a meeting with colleagues • Had a meeting with Doctor Tolu concerning Portsmouth Bot Project
Dami | • Uploaded updated data courses to Advisors academy • Made correction to RGU's Bot to handle enquiry messages and welcome properly • Review of bot conversations • Escalated a conversation on TGM Bot • Had a meeting with Doctor Tolu concerning Portsmouth Bot Project
. Thursday, 25 June 2026
Person | What Was Done | TO-DO
Totan | • Created business portfolio • Had a meeting with Doctor Tolu & Victor • Worked on a new bot [Portmouth] with AI Bot team
Victor | • Review of TGM Travels with TGM Travels Manager • Fixed bugs on TGM Travels • Deployed on TGM Travels • Configured domain function and redeployed TGM AppHub [in orer to have a proper url]
Chi | • Review Bot conversation and correct accordingly • Made changes on TGM AppHub and pushed for deployment • Review of TGM AppHub with the Head of Applications • Updated the tracking sheet while having a meeting with colleagues • Worked with Victor on fixing the URL of TGM ApphHub [Proper deployment]
Dami | • Uploaded updated data courses to Advisors academy • Creation of custom link with prefill message forPortsmouth Bot • Review of bot conversations • Collection of data [Courses for Canadian school] • Working on Portsmouth Bot [Configurations and conversational flows]
. Friday, 26 June 2026
Person | What Was Done | TO-DO
Totan | • Worked on preparation for Navitas • HWorked with Executive One Team on the platform • Worked on Customemr Serrvice platform • Trained the Portsmouth Bot on Friday
Victor | • TGM Travels
Chi | • Continued routine bot conversation reviews and performance optimization checks. • Finalized pending changes on the TGM AppHub and pushed the final stable build for deployment. • Review of the TGM AppHub platform with the Head of Applications. • Updated the tracking sheet alongside colleagues during team meetings. • Completed troubleshooting with Victor to ensure the TGM AppHub URL routing functions correctly in production.
Dami | • Worked on Portsmouth Bot • Assisted with the preparation for Portsmouth presentation
. Monday, 29 June 2026
Person | What Was Done | TO-DO
Totan | Went to the Hospital
Victor | • Worked TGM Travels platform • Had a review of TGM Travels Platform with Head of TGM Travels • Worked on Caravan (Events Platform) - created a landing page and created an adminalso n
Chi | • Had a review and changes to make on Advisors Academy app • Had a review with Head of Applications concerning the Application Dashboard an gave her access to the paltform • Finalized pending changes on the TGM AppHub and pushed the final stable build for deployment. • Updated the tracking sheet alongside colleagues during team meetings. • Completed troubleshooting with Victor to ensure the TGM AppHub URL routing functions correctly in production. • Imported, downloaded, and uploaded new leads RGU, KENT
Dami | • Bot conversation review • Worked on tgm in house counselor AI assistant • Gathering of courses to update tgm's knowlwdge base as well as to make the AI assistant knowledge base robust
. Tuesday, 30 June 2026
Person | What Was Done | TO-DO
Totan | • Worked on Finance platform • Meeting with Executive One team and added new features on the dashboard • Worked on Customemr Serrvice platform
Victor | • Worked TGM Travels platform • Had a review of TGM Travels Platform with Head of TGM Travels • Worked on Caravan (Events Platform) - created a landing page and created an admin
Chi | • Had a presentation with Doctor Tolu and GT Counsellors concerning the Application Dashboard an gave them access to the paltform. • Finalized pending changes on the TGM AppHub and pushed the final stable build for deployment. • Review of the TGM AppHub platform with the Head of Applications. • Updated the tracking sheet alongside colleagues during team meetings. • Configuration of notifications on dashboard to receive emails
Dami | • Assisted with the creation of a finance dashboard for TGM to help the compaany manage and track commission from partner schools • Made changes to executive one dashboard • Reviewed bot conversations • Handled a human handoff on the bot and escalated the potentital student to customer service • Worked on the counselor AI assistant (TGMAI)
. Wednesday, 1 July 2026
Person | What Was Done | TO-DO
Totan | • Made changes and worked on deployement for Executive One dashboard with the Exective One team • Made changes and worked on deployement for Finance dashboard • Worked on TGM Bot integration and fix the errors
Victor | • Deployed the Finance app • Updated TGM Travels admin operations • Updated admin and super admin dashboards
Chi | • Escalated a conversaton on TGM Bot • Finalized pending changes on the TGM AppHub and pushed the final stable build for deployment. • Review of the TGM AppHub platform with the Head of Applications. • Updated the tracking sheet alongside colleagues during team meetings. • Configuration of notifications on dashboard to receive emails
Dami | • Reviewed jotform integration into CRM to populate for phone number on the CRM • Worked on TGMAI (counselor AI assistant) • Review of bot conversations • Changed the file format of the document in our bot knowledge base on botpress to a markdown file
. Thursday, 2 July 2026
Person | What Was Done | TO-DO
Totan | • Changes on Executive One Dashboard • Changes on the finance platform • Prepared presentation for Chi with Chi • Meeting with Doctor Tolu
Victor | • Worked on Carvan and TGM Travels
Chi | • Meeting with Doctor Tolu on status of my current project [TGM AppHub] • Finalized pending changes on the TGM AppHub and pushed the final stable build for deployment. • Presentation with All counsellors and All Application officers of the introduction of TGM AppHub • Updated the tracking sheet alongside colleagues during team meetings. • Made enquires on changes made and new features for TGM AppHub • Bot conversation reviews and performance optimization checks.
Dami | • Deployment of TGMAI and updating of the AI knowledge-base • Reviewed Bot Conversations • Making of changes to the deployed platform
. Friday, 3 July 2026
Person | What Was Done | TO-DO
Totan | • Changes on Executive One Dashboard • Changes on the finance platform • Prepared presentation for Chi with Chi • Meeting with Doctor Tolu
Victor | • Worked on the Admin dashboard for event owner and event creator for Carvan
Chi | • Implemented the structural feedback and final platform adjustments requested by the committee. • Pushed the updated build to production and ran full system checks to guarantee everything deployed and runs smoothly. • Created and provisioned new platform user accounts for the incoming counsellors using the staff data provided by the Branch Manager, Mrs. Dami.
Dami | • Worked on TGMAI and updated the knowledge-base • Reviewed Bot Conversations • Pushed to Github abd started on the process of deployment by working with Victor
. Monday, 6 July 2026
Person | What Was Done | TO-DO
Totan | On leave
Victor | • Worked on the Admin dashboard for event owner and event creator for Carvan
Chi | • Conducted a cross-branch onboarding session with the Branch Manager, Mrs. Dami, introducing staff to the application dashboard. • Created and configured user accounts, distributed login credentials, and supported staff onboarding. • Trained a new department intern on the organization's core software platforms. • Reviewed daily team logs to monitor technical activities • Monitored AI bot conversation logs to assess response quality and system performance.
Dami | • Worked on TGMAI and updated the knowledge-base • Reviewed Bot Conversations • Pushed to Github abd started on the process of deployment by working with Victor
Ini | • Received an onboarding overview from Mr. Victor on TGM Education’s core IT solutions, including the Advisors Academy, internal chatbots, the Counsellors' AI Assistant, Caravan, and the Executive One Capital website. • Initiated development in Botpress to build and train a personalized AI chatbot designed to mirror my conversational style.
. Tuesday, 7 July 2026
Person | What Was Done | TO-DO
Totan | On leave
Victor | On leave
Chi | • Completed routine AI bot conversation reviews and checked for system errors. Audited the main application dashboard, identified several technical bugs, and successfully implemented fixes. • Programmed and deployed new custom features requested by the application officers to improve their dashboard workflow. • Partnered with Dami to design and build a new local job board dashboard called "Job Locale" (structured like Indeed) for Mr. Dotun, successfully running the initial prototype in a local environment. • Conducted a comprehensive training session with the new intern, Ini, to walk him through our development tools
Dami | • Worked on TGMAI and updated the knowledge-base • Reviewed Bot Conversations • Pushed to Github abd started on the process of deployment by working with Victor
Ini | • Completed training and initial testing for the chatbot. • Attempted the WhatsApp Business API integration and began troubleshooting deployment issues. • Attended the team presentation for the TGM Counsellors’ AI Assistant.
. Wednesday, 8 July 2026
Person | What Was Done | TO-DO
Totan | On leave
Victor | On leave
Chi | • Ran daily AI bot reviews to maintain conversational quality. • Troubleshot and resolved recurring technical bugs on the main application dashboard alongside the engineering team. • Co-hosted a platform presentation for all Counsellors to demonstrate the latest system updates and dashboard features for TGM-AI • Merged Sodiq’s new counselor dashboard (TGM-AI) into the TGM AppHub, creating a smooth redirection flow for counselors submitting applications. • Continued hands-on practical training and orientation sessions with the new intern, Ini.
Dami | • Worked on TGMAI and updated the knowledge-base • Reviewed Bot Conversations • Pushed to Github abd started on the process of deployment by working with Victor
Ini | • Continued troubleshooting the WhatsApp Business integration. • Received guidance from Ms. Chioma on utilizing actions, agents, and custom tools within TGM’s existing bot architecture. • Expanded capabilities within Botpress Studio by building workflows for practical features, including a file uploader, image reader, and audio transcriber. • Successfully deployed and integrated the chatbot into Discord for peer testing and feedback.
. Thursday, 9 July 2026
Person | What Was Done | TO-DO
Totan | On leave
Victor | On leave
Chi | • Initiated the final optimization and feature-locking process for the newly created application modules to ensure stable deployment. • Implemented specific structural updates and logic modifications on the Portsmouth bot based on guidelines provided by Dr. Tolu. • Attended a technical project review meeting with Dr. Tolu to discuss optimization strategies and next steps for the Portsmouth bot. • Performed routine AI bot checks and applied quick fixes to conversational flows where needed.
Dami | • Worked on TGMAI and updated the knowledge-base • Reviewed Bot Conversations • Pushed to Github abd started on the process of deployment by working with Victor
Ini | • Developed a structured workflow based on a message template provided by Mr. Joshua. • Configured the bot to query a knowledge base, request and validate user data, and route the conversation dynamically based on the input verification.
. Friday, 10 July 2026
Person | What Was Done | TO-DO
Totan | On leave
Victor | On leave
Chi | • Finalized the end-to-end deployment of all requested features on the live platform and ran final functionality checks to ensure optimal performance. • Completed post-deployment monitoring to confirm the application dashboard and its newly merged modules run without disruption. • Attended the company-wide Town Hall meeting and participated in departmental syncs. • Created and provisioned two extra user accounts for the Super Admin role on the platform.
Dami | • Worked on TGMAI and updated the knowledge-base • Reviewed Bot Conversations • Pushed to Github abd started on the process of deployment by working with Victor
Ini | • Began designing a workflow to capture user WhatsApp numbers, store them as variables, and reference them dynamically within active chat sessions.
. Monday, 13 July 2026
Person | What Was Done | TO-DO
Totan | • Integrated Jotsform incustomer service Dashboard • Made some changes in Executive One with the Executive One team • Bot update [for template to reach every number] • Taught Ini[Intern] Data Analytics concept and practicals
Victor | • Started Ethopian Airline API Integration for TGM Travels • Updated Caravan, added speaker feature and updated security
Chi | • AI Bot review • Merged TGM-AI into TGM AppHub and configured • Add new features and changes to TGM AppHub • Imported UCLAN Leads • Worked on a new project for R&D Department [Report Hub] • Added a new user to TGM AppHub [Developer's account]
Dami | • Confirguration of Portsmouth bot to be able to capture number of users chatting with it to enable proper function of one of the integrated workflow with Totan. • Merging of TGM-AI into TGM AppHub and configuration across pages with Chi • Review of Bot conversation. • Gathering of data to boost TGM AI Knowledge base on new locations • Follow up on a previous student from advisors • Instructing the intern
. Tuesday, 14 July 2026
Person | What Was Done | TO-DO
Totan | • Worked on customer service platform • Presentation of Portsmouth Bot to stakeholders with respective R&D Team • Meeting with Josephine concerning the customer service platform • Discussed a new proposed dashboard with Dami • Discussed a new R&D department dashboard with Chi • Worked on the finance dashboard
Victor | • Deployed the Caravan platform and review changes with the team and added some fixes accordingly
Chi | • AI Bot review • Imported, Downloaded and Uploaded KENT, NORTH & KENT Leads • Merged TGM-AI into TGM AppHub and configured and Deployed with Victor • Worked on the new changes for TGM AppHub [creation of 3 new super admins for the management] • Presentation of Portsmouth Bot to stakeholders with respective R&D Team • Added a new user to TGM AppHub [Developer's account] and deployed
Dami | • Reviewed Bot conversations and made changes to RGU's and TGM's Bot learning • Included a learning on scholarship offers for RGU's bot • Updated TGM's bot learning to have detailed direction to our expo locations. • Updated courses on advisor's academy platform • Updated the knowledge base of TGM's aI on new locations • Presentation of Portsmouth Bot to stakeholders with respective R&D Team
. Wednesday, 15 July 2026
Person | What Was Done | TO-DO
Totan
Victor | • Worked on Caravan super-admin major updates on the dasboard
Chi | • AI Bot review • Imported, Downloaded and Uploaded KENT, NORTH & KENT Leads • Merged TGM-AI into TGM AppHub and configured and Deployed with Victor • Worked on the new changes for TGM AppHub [ creation of 3 new super admins for the management] • Presentation of Portsmouth Bot to stakeholders with respective R&D Team • Added a new user to TGM AppHub [Developer's account] and deployed
Dami | • Uploading of courses to advisors platform • Review of bot conversations • Correction on learning of RGU's Bot to respond to out of context inquires • Following up on submission on Jotsform • Learning on deployment and model building • Worked on a platform for sales funnel
. Thursday, 16 July 2026
Person | What Was Done | TO-DO
Totan | • Meeting with Advisors Academy and sorting out campaigns • Worked on executive one with the executive one team • Jotsform follow-up and app review
Victor | • Worked on Caravan admin update • Had a Caravan review with Doctor Tolu • Advisors Academy with Godwin [Mobile Developer]
Chi | • AI Bot review • Review of advisors academy super admin dashboard, report preparation and submission of recommendations. • Worked on Reporting Platform • Worked on the new changes for JobLocale platform for Mr Dotun with the team
Dami | • Review of Bot conversations • Review of advisors academy super admin dashboard, report preparation and submission of recommendations. • Updated courses on advisor's academy platform for students
. Friday, 17 July 2026
Person | What Was Done | TO-DO
Totan
Victor
Chi | • AI Bot review • Imported, Downloaded and Uploaded KENT, NORTH & KENT Leads • Merged TGM-AI into TGM AppHub and configured and Deployed with Victor • Worked on the new changes for TGM AppHub [ creation of 3 new super admins for the management] • Presentation of Portsmouth Bot to stakeholders with respective R&D Team • Added a new user to TGM AppHub [Developer's account] and deployed
Dami | • Review of Bot conversations • Review of advisors academy super admin dashboard, report preparation and submission of recommendations. • Updated courses on advisor's academy platform for students
. Monday, 20 July 2026
Person | What Was Done | TO-DO
Totan | • Worked on the presentation for Potential Universities with R&D Team and Legal team [Nimi] • Worked on some changes/update on finance and legal dashboard • Showed TGM Travels team lead the Stride app being worked on
Victor | • Updated the super admin analytics; added view analytical cards • Deployed changes to the Finance dashboard • Reviewed and tested the latest changes on the mobile app • Added admin changes to Caravan
Chi | • Participated in strategic planning meetings with the R&D team and Dr. Tolu to prepare and refine product demonstration materials for upcoming collaborator presentations. • Applied initial code updates to the TGM AppHub platform in preparation for upcoming feature. • Processed inbound student lead channels by importing and downloading Northampton lead batches.
Dami | • Preparation for Portsmouth preparation • Updating of course on Advisors platform • AI Bot conversation review
. Tuesday, 21 July 2026
Person | What Was Done | TO-DO
Totan | • Prepared the presentation but the presentation was rescheduled • Worked on TGM travel app and made changes on executive one platform
Victor | • Worked on super admin changes that Dami highlighted on Advisors Acadmey platform
Chi | • Completed final presentation preparations and alignment checks ahead of product demonstration sessions. • Implemented and deployed key feature upgrades on the TGM AppHub as requested by Dr. Tolu and Mrs. Medile, including the new Deposit tracking and University Compare tools. • Collaborated with Totan and Dami on UI and structural enhancements for the Job Locale platform. • Conducted a product review and provided strategic feature feedback for Totan on the new TGM Travels application. • Evaluated and reviewed the current development progress of the Caravan platform with Victor. • Imported and downloaded lead batches for the University of Central Lancashire (UCLAN) and the University of Kent (KENT)
Dami | • Preparation for Portsmouth Bot presentation • Updating the learning on RGU bot to handle off conversations • AI Bot conversation review • Purchase of domain name for Mr Dotun's platform [JobLocale] with Totan.
. Wednesday, 22 July 2026
Person | What Was Done | TO-DO
Totan | • Bot changes with Dami • Review with Doctor Tolu on the travels app
Victor
Chi | • Worked alongside Totan to execute major updates and refinements on the Job Locale platform. • Finalized the integration of the Deposit feature and pushed key performance updates to the TGM AppHub. • Imported and downloaded lead batches for Robert Gordon University (RGU). • Formatted, compiled, and uploaded the full week’s lead data (Northampton, UCLAN, Kent, and RGU) onto the central tracking sheet.
Dami | • Preparation for Portsmouth Bot presentation • Updating the learning on RGU bot to handle off conversations • AI Bot conversation review • Purchase of domain name for Mr Dotun's platform [JobLocale] with Totan.
. Thursday, 23 July 2026
Person | What Was Done | TO-DO
Totan | CELEBRATION OF DOCTOR TOLU'S BIRTHDAY
Victor
Chi | • Collaborated directly with the Head of Applications to troubleshoot and resolve application processing issues encountered on the TGM AppHub. • Implemented system stability updates on the TGM AppHub platform to address reported user errors. • Participated in company-wide corporate activities and team celebrations for Doctor Tolu’s birthday.
Dami | CELEBRATION OF DOCTOR TOLU'S BIRTHDAY
. Friday, 24 July 2026
Person | What Was Done | TO-DO
Totan | • Had a presentation of TEUG to potential universities with the R&D TEAM • Worked on finance platform
Victor | • Had a presentation of TEUG to potential universities with the R&D TEAM
Chi | • Participated in an executive review and demonstration of the TGM AppHub with Mr. Donald and the R&D team to gather high-level feedback. • Joined the R&D team in presenting the TEUG platform to potential partner universities. • Implemented all requested structural changes and feature refinements highlighted by Mr. Donald during the review. • Conducted routine AI bot conversation audits and performance quality checks.
Dami | • Had a presentation of TEUG to potential universities with the R&D TEAM
. Monday, 27 July 2026
Person | What Was Done | TO-DO
Totan | • Worked on the presentation for Potential Universities with R&D Team and Legal team [Nimi] • Worked on some changes/update on finance and legal dashboard • Showed TGM Travels team lead the Stride app being worked on
Victor
Chi | • Worked on new changes on AppHub
Dami | • Meeting with Doctor Tolu, Mr Donald and Totan on briefing for the October 2026 road show campaign • Updating of courses on Advisors to prepare for 2027 intake session • AI Bot conversation review
. Tuesday, 28 July 2026
Person | What Was Done | TO-DO
Totan | • Worked on the presentation for Potential Universities with R&D Team and Legal team [Nimi] • Worked on some changes/update on finance and legal dashboard • Showed TGM Travels team lead the Stride app being worked on
Victor
Chi | • Worked on new changes on AppHub • Meeting with Doctor Tolu, review of bot learning, AppHub, Caravan, engaging in AppHub presentation of solutions built so far • Gave reviews on Caravan and worked on new changes with Victor on Caravan
Dami | • Meeting with Doctor Tolu, review of bot learning, AppHub, Caravan, engaging in presentation of solutions built so far • Meeting with Mr Donald to get briefing on campaign and needed into to train the campaign bot • AI Bot conversation review
. Wednesday, 29 July 2026
Person | What Was Done | TO-DO
Totan | • Worked on the presentation for Potential Universities with R&D Team and Legal team [Nimi] • Worked on some changes/update on finance and legal dashboard • Showed TGM Travels team lead the Stride app being worked on
Victor
Chi | • Worked on new changes on AppHub with Totan • Had a meeting with Mr Donald concerning new update on the AppHub • Meeting with Doctor Tolu, review of bot learning, AppHub, Caravan, engaging in AppHub presentation of solutions built so far
Dami | • Modified, corrected and updated the learning for the campaign bot • Setting up of the whatsapp manager account for the bot campaign number • Worked on a new platform [TGM Community] with Totan • AI Bot conversation review
. Thursday, 30 July 2026
Person | What Was Done | TO-DO
Totan | • Worked on the presentation for Potential Universities with R&D Team and Legal team [Nimi] • Worked on some changes/update on finance and legal dashboard • Showed TGM Travels team lead the Stride app being worked on
Victor
Chi | • Worked on new changes on AppHub with Totan • Had a meeting with Mr Donald concerning new update on the AppHub • Meeting with Dr Tolu on changes to be made on Apphub
Dami | • Review of bot conversations across bots • Meeting with Dr Tolu on changes to be made on Apphub and presentation of backend for the TGM AI • Modification of Campaign bot learning • Learning on deployment to digitalocean, worked on TGM community with Totan
. Friday, 31 July 2026
Person | What Was Done | TO-DO
Totan | • Worked on executive one chnages • Worked on finance dashboard and made some updates • Bot creation for campaign • Foloow-up on customer service
Victor
Chi | • Worked on new changes on AppHub with Totan
Dami | • Review of bot conversations on the campaign bot and across other bots • Addition of learning on the campaign bot to respond accurately to persons willing to begin their application process (communication of needed documents and forward of link to collect their submission) • Escalation of a complaint from a student on the tgm bot to Totan. • Addition of human handoff procedure to the campaign bot (human in the loop) if needed. • Worked a on TGM community (a new platform) • Modification of the learning on TGM bot answer properly on the upcoming exhibition.
. Monday, 3 August 2026
Person | What Was Done | TO-DO
Totan | • Worked on executive one chnages • Follow ups with legal and R&D Department • Built a migration flow for campaign bot
Victor | • Depaa • Had
Chi | • Had a meeting with application head [Shola] on the new changes on TGM AppHub that has been published • Had a meeting with Mr Donald on the new changes on TGM AppHub • Had a meeting with Mrs Medile on the new changes on TGM AppHub and made corrections to these changes • Imported and downloaded leads for RGU, KENT, UCLAN & NORTH
Dami | • Review of bot conversations on the campaign bot and across other bots • Addition of learning on the campaign bot to respond accurately to persons willing to begin their application process (communication of needed documents and forward of link to collect their submission) • Escalation of a complaint from a student on the tgm bot to Totan. • Addition of human handoff procedure to the campaign bot (human in the loop) if needed. • Worked a on TGM community (a new platform) • Modification of the learning on TGM bot answer properly on the upcoming exhibition.
. Tuesday, 4 August 2026
Person | What Was Done | TO-DO
Totan | • Worked on executive one chnages • Follow ups with legal and R&D Department • Built a migration flow for campaign bot
Victor | • Depaa • Had a meeting with application head [Shola] on the new changes on TGM AppHub
Chi | • Had a meeting with application head [Shola] on the new changes on TGM AppHub that has been published • Had a meeting with Mr Donald on the new changes on TGM AppHub • Had a meeting with Mrs Medile on the new changes on TGM AppHub and made corrections to these changes • Imported and downloaded leads for RGU, KENT, UCLAN & NORTH
Dami | • Review of bot conversations on the campaign bot and across other bots • Addition of learning on the campaign bot to respond accurately to persons willing to begin their application process (communication of needed documents and forward of link to collect their submission) • Escalation of a complaint from a student on the tgm bot to Totan. • Addition of human handoff procedure to the campaign bot (human in the loop) if needed. • Worked a on TGM community (a new platform) • Modification of the learning on TGM bot answer properly on the upcoming exhibition.

## 📊 Dashboard
9 | Project Lead | Status | % Done | Start Date | Deadline | Impact | KEY METRICS
Bot Building | Totan/Chi | in Progress | 100% | 23/02/2026 | 29/05/2026 | Optimise lead conversion flows; integrate CRM for lead tracking & reporting | COMPLETED
Advisors Academy | Totan | In Progress | 90% | 27/04/2026 | Undecided | Expand university partnerships & launch student agent recruitment campaign | IN PROGRESS
HR App | Victor/Totan | In Progress | 70% | Undecided | 26/06/2026 | Final QA testing & company-wide staff onboarding training session | IN PROGRESS
Roadshow Registration Dashboard | Totan | In Progress | 50% | Undecided | 26/06/2026 | Plan V2 with SMS notifications, self-check-in kiosk & WhatsApp reminders | IN PROGRESS
Application Hub (Application Dashboard) | Chi | In Progress | 80% | 18/05/2026 | Undecided | Finish deployment testing, resolve duplicate rows and roll out to the full application team | IN PROGRESS
TGM Travels | Victor | Not Started | 0% | Undecided | Undecided |  | NOT STARTED
Executive One Dashboard & Bot | Totan/Chi | In Progress | 50% | 17/06/2026 | Undecided | Finalise bot automation, complete dashboard polish and present to leadership | IN PROGRESS
In-House Counsellor Bot | Dami/Chi | In Progress | 40% | 04/06/2026 | Undecided | Continue training, test responses with counsellors and refine knowledge base | IN PROGRESS
AI Policy Checker | Totan | Completed | 100% | 15/06/2026 | 16/06/2026 | Monitor in use and update rules as policies evolve | COMPLETED
AI Travel Assistant | Dami | Not Started | 0% | Undecided | Undecided |  | NOT STARTED

## advisors academy platform
Task | Description | Module | Date documented | Start Date | End date
Study mode | Study mode list has alot of redundant and needless selections let us get rid of it | Student and counsellors | 30/7/2026 ( though this had beenmentioned a month before but wasnt attended too)
Search optimization | move the university search tab forward so that when they wan tto search they can search through the available universities. then under tge enter keyword it should not be a drop down or no suggestion should be given at the moment this drop down irrespective of which university you pick it would still show the wrong options as it would bring out any university in the DB | Student and counsellors | 30/7/2026
Statement of purpose (accept word document) | The statement of purpose tab should accept workd document format |  | 30/7/2026

## Bot Change Log
Date | Bot Name | Change Type | Short Summary | Detailed Description (What was changed, why and how)
04-Jun-2026 | All Bots | Behaviour Rule | Stop repeating user names | Bot was using the student's name repeatedly and incorrectly; including using it as a project label. Instruction added: never use the full name, use only the first name once where natural, and normalise capitalisation if student types in all caps.
| TGM Bot | Instruction Update | Converse more humanly | Bot responses were robotic and AI-sounding at the Data collection field because it was sounding like AI
| All Bots | New Feature | Audio transcription added | Added WhatsApp voice note transcription using OpenAI Whisper API. Bot can now receive audio messages, transcribe them and respond. Implemented via Botpress Execute Code node with FormData and axios.
| All Bots | Instruction Update | Countries not in TGM partnership | Added instruction for countries outside TGM's network (UK, Ireland, Canada, USA, Australia, Germany, Poland). Bot no longer shuts down the conversation. Instead it warmly steers students toward the most suitable TGM partner country for their goals.
| All Bots | Behaviour Rule | Off-topic conversation handling | Added rule for conversations unrelated to TGM money requests, inappropriate content, document writing, irrelevant services. Bot redirects calmly and professionally without engaging, lecturing or entertaining the message.
| TGM Bot | Knowledge Base | TGM address added | Added TGM Education physical address to knowledge base so bot can respond when students ask where TGM is located or how to visit.
| UCLan Bot | Greeting Update | Initial greeting updated | Shortened opening message to: 'Welcome to the University of Lancashire; let's start your study abroad journey! What's your name?'
| All Bots | Instruction Update | Name address rules updated | Updated across all bots: never use student's full name. Use first name only once where natural. Most responses should not include name at all. If student types name in all caps, normalise to first-letter capitalisation only.
TGM Bot
04-Jun-2026 | TGM Bot | Behaviour Rule | Read before responding. | Added instruction telling the bot to read the full message before replying and never ask for information already provided. Bot was ignoring context in the same message. Fixed by adding a rule: if the student already stated a detail, use it directly without asking again.
2026-06-08 | TGM, RGU, UCLAN Bot | New Feature | Vision enabled to read images | Enabled AI Vision on TGM, RGU and UCLan bots. Bots can now read and understand images sent by students and respond based on the content of the image.
| TGM Bot | Knowledge Base | TGM office addresses added | Added TGM Education's Head Office in Lagos and all branch locations to the knowledge base: Abuja, Benin, Uganda, Ibadan, Kano, Port Harcourt and Ghana. Bot can now respond when students ask where TGM is located or how to visit any office.
| All Bots | Knowledge Base | Study Abroad Expo date and time added | Added the confirmed date and time for the Study Abroad Fair to the knowledge base. Bot can now correctly inform students about when the expo is happening when asked.
| Northampton Bot | Bug Fix | Application link corrected | The application link for the University of Northampton was incorrect. Corrected and replaced with the right link so students are directed to the proper registration page when they want to apply.
| TGM Bot | Instruction Update | Dependant visa degree requirement added | Bot was not advising students correctly on which programmes qualify for bringing dependants. Added instruction that only research programmes; MRes, MPhil, PhD and similar; qualify for the dependant visa route. Bot now guides students accordingly when they ask about studying with family.
2026-06-09 | TGM Bot | Instruction Update | Service fee updated to free | Updated instruction to make clear that all TGM Education services are completely free. Bot now responds with confidence that there is no service charge when students ask.
| TGM Bot | Instruction Update | Team response time corrected to 24 hours | Bot was saying the team responds within "a few business days" which is incorrect. Updated instruction so bot now always states the team will reach out within 24 hours to confirm application details.
| NORTH, KENT, NAVITAS | New Feature | Vision enabled | Enabled AI Vision on Northampton, Kent and ICP Navitas bots. Bots can now read and understand images sent by students and respond based on the image content.
| RGU, UCLAN, NORTH, KENT | Knowledge Base | Physical address added | Added TGM Education's Lagos Head Office address to the knowledge base of RGU, UCLan, Northampton and Kent bots. Students who ask where to visit or find TGM will now be directed to the Lagos Head Office.
2026-06-09 | RGU Bot | Bot Training | RGU bot training session | Held a bot training session with the team on the RGU bot, working through its conversation flow to improve how it responds to students.
| TGM, RGU Bot | New Feature | Image and video feature added | Added an image and video feature to the TGM and RGU bots so they can send images and videos to students during a conversation, not just text.
| Kent, Navitas, Northampton Bot | New Feature | Vision agent enabled | Enabled the AI Vision agent on the Kent, ICP Navitas and Northampton bots so they can read and understand images sent by students and reply based on what is in the image.
| All Bots | Instruction Update | Trained on counsellor chats | Gathered chat data from the top counsellors and used it to train the bots so their conversation sounds more natural and closer to how a real counsellor speaks.
2026-06-15 | All Bots | New Feature | WhatsApp integration upgraded | Upgraded the WhatsApp integration across all bots to improve how they connect and respond to students on WhatsApp.
| RGU, Northampton, Kent, UCLan Bot | New Feature | Translator agent enabled | Enabled translator agents on the RGU, Northampton, Kent and UCLan bots so they can understand and respond to students in other languages.
2026-06-16 | Kent Bot | Bug Fix | Nudge sequence corrected | The nudge sequence on the Kent bot was not working as intended. Corrected the sequence so the bot follows up with students at the right time.
| All Bots | Knowledge Base | New courses and fees uploaded | Uploaded newly gathered courses and fees for several partner universities to the bots so they can give students up-to-date course and fee information.
2026-06-18 | RGU, Northampton, Kent, UCLan Bot | Profile Update | WhatsApp profile pictures updated | Updated and designed new WhatsApp profile pictures for the RGU, Northampton, Kent and UCLan bots to give each one a clean, branded look on WhatsApp.
2026-07-30 | Campaign bot | Greeting Update | Configuration of the greeting to engage immediately on the october roadshow. | The learning instruction was configured based on prefilled mesage coming in from the campaign landing page.
|  | Instruction Update | Updated the instruction, to respond based on campaign enquiries, location, perks, schorlarship offers/discounts on tuition, roadshow locations, intakes and available schools at the roadshow.
|  | Behaviour Rule | updated the bot learning to never admit to be a bot or an AI assistant | slated plainly in the bot instructions
|  | Knowledge Base | knowledge base was populated with frequently asked questions as regard study abroad process, documents, intakes, visa processing time, loans. | knowledge base was curated and existing ones were tranferred to the new bot.

## Northampton- KB LOG
Knowledge Base Name | Type | Date Added / Created | Status | Remarks | Notes
uni_of_north.txt | PDF | Created 4 months ago | ✅ Active | University information document | New IELTS policy
Rich Text File | Rich Text | Created 4 days ago | Active | General rich text content | General guide
Dependant laws | Rich Text | Created 3 months ago | Active | Dependant laws information | Updated locations
wait time | Rich Text | Created 3 months ago | Active | Wait time information | New courses added
Rich Text File | Rich Text | Created 3 months ago | Active | Additional rich text content | Updated awards
visa fees | Rich Text | Created 3 months ago | Active | Visa fee information | New residences
Location | Rich Text | Created 3 months ago | Active | Location details | Updated tuition
CAS Payment | CAS Payment | Created 3 months ago | Active | CAS Payment | CAS Payment
Courses | Rich Text | Created 3 months ago | Active | Information on available courses | Information on available courses
Visa fees | Rich Text | Created 3 months ago | Active | Visa application fee information | Visa application fee information
Weather | Rich Text | Created 4 months ago | Active | Weather information | Weather information
Refer wallet | Rich Text | Created 4 months ago | Active | Referral wallet details | Referral wallet details
Cost of living | Rich Text | Created 4 months ago | Active | Cost of living estimates | Cost of living estimates
Proof of funds | Rich Text | Created 4 months ago | Active | Proof of funds requirements | Proof of funds requirements
UK VISA FEES | Rich Text | Created 4 months ago | Active | UK visa fee schedule | UK visa fee schedule

## AACADEMY- KB LOG
KB Name | Document Type | Purpose/Description | Date Added | Last Updated | Status
KB Name | Document Type | Purpose/Description | Date Added | Last Updated | Status
ReferWallet_KnowledgeBase (1).docx | Word Document | ReferWallet knowledge base documentation | Created 21 days ago | - | Active
issues with google login | Rich Text | Google login troubleshooting guide | Created 1 month ago | - | Active
Advisors_Academy_User_Guide.docx | Word Document | Advisors Academy user manual | Created 1 month ago | - | Active
TGM PARTNERED SCHOOLS.pdf | PDF | Partnered schools information | Created 9 months ago | - | Active
Application Document Requirements for Different Countries.pdf | PDF | Country-specific application requirements | Created 9 months ago | - | Active
UK ACCOMMODATION INFO.pdf | PDF | Accommodation information for the UK | Created 9 months ago | - | Active
UK WEATHER.pdf | PDF | UK weather overview | Created 9 months ago | - | Active
weather data.pdf | PDF | Weather data and climate information | Created 9 months ago | - | Active
post study.pdf | PDF | Post-study opportunities and guidance | Created 9 months ago | - | Active
Dependent Visa Laws for International Students.pdf | PDF | Information on dependent visa laws | Created 9 months ago | - | Active
Work Opportunities for International Students.pdf | PDF | Employment opportunities for international students | Created 9 months ago | - | Active
International Education & Visa Terminology.pdf | PDF | Educational and visa terminology guide | Created 9 months ago | - | Active
Visa Fees for International Students by Country.pdf | PDF | Country-specific visa fee information | Created 9 months ago | - | Active
Living Expenses.pdf | PDF | Living cost estimates and guidance | Created 9 months ago | - | Active
International Tuition Fees.pdf | PDF | Tuition fee information | Created 9 months ago | - | Active
Document Creation for Study Abroad Applications.pdf | PDF | Application document preparation guide | Created 9 months ago | - | Active
Family_Friendly_Cities.pdf | PDF | Family-friendly city information | Created 9 months ago | - | Active
Dependant laws.docx | Word Document | Dependant visa regulations | Created 9 months ago | - | Active
Frequently Asked Questions.pdf | PDF | General FAQ resource | Created 9 months ago | - | Active
AA.BOT (1).pdf | PDF | AI Bot reference documentation | Created 10 months ago | - | Active
AA.BOT.pdf | PDF Document | AI Bot reference and knowledge base document | Created 10 months ago | – | Active

## UCLAN- KB LOG
Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9
Document Name | Category | Description / Purpose | Date Added | Last Updated |  | Owner | Status | Notes
Dependant laws | Visa & Immigration | Information about dependent visa rules and regulations. | 2025-03-08* | - |  |  | Active
Wait time | Visa Processing | Visa application processing timelines. | 2025-03-08* | - |  |  | Active
Location | General Information | Office, university, or destination location details. | 2025-03-08* | - |  |  | Active
Course details | Education | Information about available courses and requirements. | 2025-03-08* | - |  |  | Active
Refer wallet | Referral Program | Details about referral wallet and rewards. | 2025-03-08* | - |  |  | Active
Cost of living | Student Information | Living expenses and budgeting information. | 2025-03-08* | - |  |  | Active
Proof of funds | Visa Requirements | Financial evidence requirements for visa applications. | 2025-03-08* | - |  |  | Active
UK VISA FEES | Visa Fees | Current UK visa fee structure. | 2025-03-08* | - |  |  | Active

## NAVITAS- KB LOG
KB ID | File Name | Type | Category | Description | Date Added | Size | Status | Owner | Last Review | Notes
ICP_Job_Opportunity_Guide.docx | DOCX | Employment | Job opportunities and employment guidance | Created 1 month ago | 0.20 MB | Active
Key selling points for University of Portsmouth.pdf | PDF | University Information | University selling points and benefits | Created 1 month ago | 3.96 MB | Active
UK_Student_Visa_Bot_Script2.pdf | PDF | Visa Process | Student visa script and FAQs | Created 1 month ago | 4.09 MB | Active
Lagos_to_Portsmouth_Travel_Guide.docx | DOCX | Travel | Travel guidance for students | Created 1 month ago | 0.04 MB | Active
Portsmouth_Nigerian_Food_Guide.docx | DOCX | Lifestyle | Nigerian food options in Portsmouth | Created 1 month ago | 0.04 MB | Active
Universities Knowledge base.pdf | PDF | Universities | General university information | Created 1 month ago | 0.33 MB | Active
navitas_kb_full.pdf | PDF | Navitas | Complete Navitas knowledge base | Created 1 month ago | 8.01 MB | Active
Navitas Knowledge base.pdf | PDF | Navitas | Navitas information repository | Created 1 month ago | 7 MB | Active
icp navitas knowledge base.pdf | PDF | Navitas | ICP/Navitas information | Created 1 month ago | 7.43 MB | Active
Search the web #1 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #2 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #3 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #4 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #5 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #6 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #7 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #8 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #9 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Search the web #10 | Web Search | External Sources | Web search reference | Added 1 month ago | N/A | Active
Rich Text File | Rich Text | Internal Notes | Custom written content | Created 20 days ago | N/A | Active

## RGU- KB LOG
Column 1 | Item Name | Date Added | Content Owner | Last Updated | Review Frequency | Next Review Date | Status
RGU NEW DEPOSIT | 3 hours ago | - | - | Monthly | Monthly | Active
refer wallet | 21 days ago | - | - | Quarterly | Quarterly | Active
OFFICE LOCATION | 3 months ago | - | - | Quarterly | Quarterly | Active
Submission link | 3 months ago | - | - | Monthly | Monthly | Active
Dependant law | 3 months ago | - | - | Monthly | Monthly | Active
Visa fees | 4 months ago | - | - | Monthly | Monthly | Active
Proof of funds | 4 months ago | - | - | Monthly | Monthly | Active
UK WEATHER | 4 months ago | - | - | Quarterly | Monthly | Active
Accomodation | 4 months ago | - | - | Quarterly | Monthly | Active
Intake periods | 4 months ago | - | - | Monthly | Monthly | Active